## Sheet4
Values
Sprint Name | Sum of Committed | Sum of Delivered
DAP Registry Platform Sprint 0 | 3 | 0
DAP Registry Platform Sprint 1 | 3 | 0
DAP Registry Platform Sprint 2 | 21 | 13
DAP Registry Platform Sprint 3 | 16 | 16
DAP Registry Platform Sprint 4 | 66 | 66
DAP Registry Platform Sprint 5 | 21 | 21
DAP Registry Platform Sprint 6 | 26 | 0
Grand Total | 156 | 116
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Sheet1
Issue key | Sprint Name | Committed | Delivered | Status | Borad Name
PP-10306 | DA DTP Platform Sprint 4 | 3 | 3 | Closed | DA DTP Platform
PP-10272 | DA DTP Platform Sprint 2 | 5 | 5 | Closed | DA DTP Platform
PP-10294 | DA DTP Platform Sprint 4 | 8 | 8 | Closed | DA DTP Platform
PP-10000 | DA DTP Platform Sprint 4 | 5 | 5 | Closed | DA DTP Platform
PP-10499 | DA DTP Platform Sprint 4 | 2 | 2 | Closed | DA DTP Platform
PP-10457 | DA DTP Platform Sprint 3 | 5 | 5 | Closed | DA DTP Platform
PP-9718 | DA DTP Platform Sprint 1 | 2 | 0 | Development Complete | DA DTP Platform
PP-10269 | DA DTP Platform Sprint 3 | 8 | 8 | Closed | DA DTP Platform
PP-10001 | DA DTP Platform Sprint 6 | 3 | 0 | Development In Progress | DA DTP Platform
PP-10677 | DAP Registry Platform Sprint 6 | 5 | 0 | Testing In Progress | DAP Registry Platform
PP-10638 | DA DTP Platform Sprint 5 | 5 | 0 | Testing In Progress | DA DTP Platform
PP-9809 | DA DTP Platform Sprint 6 | 5 | 0 | Development Complete | DA DTP Platform
PP-10485 | DA DTP Platform Sprint 6 | 3 | 0 | Development In Progress | DA DTP Platform
PP-10869 | DA DTP Platform Sprint 6 | 3 | 0 | Development In Progress | DA DTP Platform
PP-10812 | DA DTP Platform Sprint 5 | 5 | 5 | Closed | DA DTP Platform
PP-10290 | DA DTP Platform Sprint 5 | 5 | 5 | Closed | DA DTP Platform
PP-10731 | DA DTP Platform Sprint 5 | 8 | 8 | Closed | DA DTP Platform
PP-10487 | DA DTP Platform Sprint 6 | 5 | 0 | Open | DA DTP Platform
PP-10650 | DAP Registry Platform Sprint 6 | 5 | 0 | Development In Progress | DAP Registry Platform
PP-10724 | DAP Registry Platform Sprint 6 | 3 | 0 | Open | DAP Registry Platform
PP-10396 | DAP Registry Platform Sprint 6 | 5 | 0 | Reopened | DAP Registry Platform
PP-10649 | DAP Registry Platform Sprint 6 | 8 | 0 | Development In Progress | DAP Registry Platform
PP-10291 | DA DTP Platform Sprint 2 | 3 | 0 | Reopened | DA DTP Platform
PP-10291 | DA DTP Platform Sprint 6 | 3 | 0 | Reopened | DA DTP Platform
PP-10646 | DA DTP Platform Sprint 5 | 3 | 3 | Closed | DA DTP Platform
PP-10811 | DAP Registry Platform Sprint 5 | 5 | 5 | Closed | DAP Registry Platform
PP-10903 | DAP Registry Platform Sprint 5 | 3 | 3 | Closed | DAP Registry Platform
PP-10915 | DAP Registry Platform Sprint 5 | 3 | 3 | Closed | DAP Registry Platform
PP-10916 | DAP Registry Platform Sprint 5 | 2 | 2 | Closed | DAP Registry Platform
PP-9409 | DA DTP Platform Sprint 1 | 5 | 0 | Closed | DA DTP Platform
PP-9409 | DA DTP Platform Sprint 3 | 5 | 5 | Closed | DA DTP Platform
PP-10619 | DAP Registry Platform Sprint 5 | 8 | 8 | Closed | DAP Registry Platform
PP-10295 | DA DTP Platform Sprint 4 | 8 | 8 | Closed | DA DTP Platform
PP-10438 | DAP Registry Platform Sprint 4 | 8 | 8 | Closed | DAP Registry Platform
PP-10437 | DAP Registry Platform Sprint 4 | 5 | 5 | Closed | DAP Registry Platform
PP-10434 | DAP Registry Platform Sprint 4 | 5 | 5 | Closed | DAP Registry Platform
PP-10481 | DAP Registry Platform Sprint 4 | 5 | 5 | Closed | DAP Registry Platform
PP-10480 | DAP Registry Platform Sprint 4 | 3 | 3 | Closed | DAP Registry Platform
PP-10479 | DAP Registry Platform Sprint 4 | 8 | 8 | Closed | DAP Registry Platform
PP-10478 | DAP Registry Platform Sprint 4 | 3 | 3 | Closed | DAP Registry Platform
PP-10473 | DAP Registry Platform Sprint 4 | 3 | 3 | Closed | DAP Registry Platform
PP-10468 | DAP Registry Platform Sprint 4 | 5 | 5 | Closed | DAP Registry Platform
PP-10462 | DAP Registry Platform Sprint 4 | 7 | 7 | Closed | DAP Registry Platform
PP-10433 | DAP Registry Platform Sprint 4 | 2 | 2 | Closed | DAP Registry Platform
PP-10460 | DAP Registry Platform Sprint 4 | 3 | 3 | Closed | DAP Registry Platform
PP-10426 | DAP Registry Platform Sprint 4 | 3 | 3 | Closed | DAP Registry Platform
PP-10419 | DAP Registry Platform Sprint 4 | 3 | 3 | Closed | DAP Registry Platform
PP-10459 | DAP Registry Platform Sprint 4 | 3 | 3 | Closed | DAP Registry Platform
PP-10507 | DA DTP Platform Sprint 3 | 5 | 5 | Closed | DA DTP Platform
PP-10293 | DA DTP Platform Sprint 3 | 8 | 8 | Closed | DA DTP Platform
PP-10292 | DA DTP Platform Sprint 3 | 8 | 8 | Closed | DA DTP Platform
PP-10494 | DAP Registry Platform Sprint 3 | 5 | 5 | Closed | DAP Registry Platform
PP-10495 | DAP Registry Platform Sprint 3 | 5 | 5 | Closed | DAP Registry Platform
PP-10305 | DAP Registry Platform Sprint 2 | 3 | 0 | Closed | DAP Registry Platform
PP-10305 | DAP Registry Platform Sprint 3 | 3 | 3 | Closed | DAP Registry Platform
PP-10456 | DAP Registry Platform Sprint 3 | 3 | 3 | Closed | DAP Registry Platform
PP-10235 | DA DTP Platform Sprint 2 | 5 | 5 | Closed | DA DTP Platform
PP-9875 | DA DTP Platform Sprint 1 | 2 | 2 | Closed | DA DTP Platform
PP-9276 | DA DTP Platform Sprint 1 | 8 | 8 | Closed | DA DTP Platform
PP-9067 | DA DTP Platform Sprint 1 | 3 | 3 | Closed | DA DTP Platform
PP-9584 | DA DTP Platform Sprint 1 | 7 | 7 | Closed | DA DTP Platform
PP-10367 | DA DTP Platform Sprint 2 | 8 | 8 | Closed | DA DTP Platform
PP-9848 | DAP Registry Platform Sprint 0 | 3 | 0 | Testing In Progress | DAP Registry Platform
PP-9848 | DAP Registry Platform Sprint 1 | 3 | 0 | Testing In Progress | DAP Registry Platform
PP-9857 | DAP Registry Platform Sprint 2 | 5 | 5 | Closed | DAP Registry Platform
PP-10115 | DAP Registry Platform Sprint 2 | 5 | 5 | Closed | DAP Registry Platform
PP-9694 | DAP Registry Platform Sprint 2 | 3 | 3 | Closed | DAP Registry Platform
PP-9852 | DAP Registry Platform Sprint 2 | 5 |  | Closed | DAP Registry Platform